## Project Timeline
2020 WCM-SCH National Meeting | [8 empty] | This is a modified form of a Gantt chart which focuses on creating a project schedule that is broken down into stages.
TITLE |  | 2020 WCM-SCH National Meeting Planning Team Chart |  | LOCATION | [5 empty] | Madison, WI (Tentative)
PLANNING CO-LEADS |  | Paula Cognitore, Michelle Mead, Nick Petro, Megan Syner |  | DATE | [5 empty] | June 23-25, 2020 (Chart created 01/14/20)
PHASE |  |  | DETAILS | Q1 | [12 empty] | Q2 | [12 empty] | Q3
|  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT
| PROJECT WEEK: |  | First Monday of each month --> | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5
1 | Session Draft |  | - Initiate Team Lead Meeting | JAN 27: Co-Leads Meet with Session Leads; JUN 22: NATIONAL MEETING; OCT 5: PROJECT END OCT 1
|  |  | - Initiate Session Team Meetings | FEB 10: Session Team Meetings
2 | Session Design |  | - Session Activties | FEB 10: Outline activities for session
|  |  | - Identify Facilitator(s)/Speaker(s) | FEB 24: Identify facilitators and speakers
|  |  | - Draft Session Plan/Logistics | MAR 2: Draft of Session Plan Due by 6 April 2020
3 | Finalize Session Plan |  | - Full Team Check-In | MAR 23: Full Planning Team Check-In
|  |  | - Confirm Logistics/Finalize Plan | APR 13: Confirm/Finalize Plan by 8 May 2020
|  |  | - Create Day-Of Session Checklist | MAY 11: Create session/meeting checklists
4 | Deliver Session |  | - Identify Notetaker(s) | MAY 18: Identify notetaker(s)
|  |  | - Identify Timekeeper | MAY 18: Identify timekeeper
5 | Follow-Up Actions |  | - Postmortem | JUN 29: Postmorem
|  |  | - Team Feedback | JUL 13: Team Feedback
|  |  | - Follow-Up on Actions | AUG 3: Complete follow-up on actions via VLAB