## Sheet1
Partnership Project | Required (Y/N)? | Important History (What has been done?) | Upcoming Activities | STI Follow Up Actions | NWS POC | NWS funds? | NOAA Stakeholders | STI Messaging (Comm/Outreach) - Past and Future
Partnership Project | Required (Y/N)? | Important History (What has been done?) | Upcoming Activities | STI Follow Up Actions | NWS POC | NWS funds? | NOAA Stakeholders | STI Messaging (Comm/Outreach) - Past and Future
Storm Surge | Y | 1. Creation of new products: Innundation map, storm surge warning graphic | FY15-Q3: ETSS 2.0 (NCEP implementation – May 19) (HSS funded): * Supports “Consistent Products and Services” by providing operational total water level guidance at coastal stations to RFCs. * Supports “Consistent Products and Services” by providing extra-tropical based inundation (based only on surge) guidance for the East Coast and Gulf of Mexico for use by a future extra-tropical storm surge watch and warning. FY15-Q3: P-Surge 2.5 (NCEP implementation – Jun 2) (HSS funded): * Supports AOP Milestone 05-70-15-12 (STI) by producing 2.5 km data allowing the data to be more readily into AWIPS at a national level * Supports “Consistent Products and Services” by providing 1-hr incremental exceedance above datum data to NWPS (as a surge + tide surface condition) and RFCs (as a boundary condition) allowing consistency between guidance products. FY15-Q4: ETSS 2.1 (NCEP implementation – Sep 8) (HSS funded): * Supports AOP Milestone 05-05-15-14 (STI) by replacing the extra-tropical basins for the Bering Sea and Arctic with a single basin thereby allowing modeled surge to traverse the Bering Strait * Supports “Consistent Products and Services” by providing extra-tropical based inundation (based on surge and tide) guidance for the east coast; Gulf of Mexico; and western and northern Alaska for use by a future extra-tropical storm surge watch and warning. FY15-Q3: P-Surge 2.5 (NCEP implementation – Jun 2) (HSS funded): * Supports AOP Milestone 05-70-15-12 (STI) by producing 2.5 km data allowing the data to be more readily into AWIPS at a national level * Supports “Consistent Products and Services” by providing 1-hr incremental exceedance above datum data to NWPS (as a surge + tide surface condition) and RFCs (as a boundary condition) allowing consistency between guidance products. FY15-Q4: ETSS 2.1 (NCEP implementation – Sep 8) (HSS funded):* Supports AOP Milestone 05-05-15-14 (STI) by replacing the extra-tropical basins for the Bering Sea and Arctic with a single basin thereby allowing modeled surge to traverse the Bering Strait * Supports “Consistent Products and Services” by providing extra-tropical based inundation (based on surge and tide) guidance for the east coast; Gulf of Mexico; and western and northern Alaska for use by a future extra-tropical storm surge watch and warning. FY16-Q2: P-ETSS 1.0 and ETSS 2.2 (NCEP implementation – Mar 22, 2016) (HSS funded): * Supports “S&T: Situational Knowledge” by replacing the extra-tropical basins for the Gulf of Alaska and West Coast with a single basin, thereby allowing modeled surge to travel along the Canadian coast * Supports “Consistent Products and Services” by providing probabilistic extra-tropical based inundation guidance for the east coast; Gulf of Mexico; western and northern Alaska; and Gulf of Alaska and west coast for use by a future extra-tropical storm surge watch and warning. FY16-Q3: P-Surge 2.6 (NCEP implementation – Apr 5, 2016) (HSS funded): * Support proposed FY16 AOP milestone by extending the lead time for which P-Surge is run. | Coordinate non-HSS funded milestones and activity for FY16: The next Psurge upgrade may include longer lead times, 5% exceedance, nested grid capability, and/or multiple simultaneous landfalls. | MDL: Arthur Taylor. AFS: Mark Tew, Mike Dion. NHC: Jamie Rhome. STI: Nicole Kurkowski | Y (HFIP). FTE: 2 @MDL, 1 @NHC. MDL:2 contractors (not part of O&M). NHC hiring a second FTE. NWS may (NHC can clarify) be funding 4 of NHC’s 7 contractors (WB, CFritz, TS, EG, CForbes, BZ, NH). It is believed that: (a) FEMA funds 3 of them (WB, CFritz, TS), (b) NOS had funded 1 of them (EG), but NWS/STI may be doing so now, (c) HSS had funded 1 (NH) to work on the storm surge watch / warning, but NWS/STI may be doing so now, (d) the remaining 2 (CForbes, BZ) may be funded by HFIP. | NWS Regions: ER, SR, WR, AR, PR NWS RFCs: NE-RFC, MA-RFC, SE-RFC, LM-RFC, WG-RFC, CN-RFC, NW-RFC, AP-RFC. Unkown: PR, VI, HI NWS WFOs: {CAR, GYX, BOX, OKX, PHI, LWX, AKQ, MHX, ILM, CHS}; { JAX, MLB, MFL, KEY, TBW, TAE, MOB, LIX, LCH, HGX, CRP, BRO, EWX (backup to BRO/CRP), SJU}; {SHX, LOX, MTR, EKA, PQR, SEW}; { AJK, AFC, AFG}, { HNL, GUAM, PPG} NWS Centers: NHC, OPC NWS Dev Labs: STI/MDL, STI/NCEP/EMC NWS/AFS Programs: Marine and Coastal, Tropical, Winter, Hydrology NOS: CO-OPS, OCS, OCM, IOOS; OAR: Sea Grant NWS/AFS, STI/MDL, NCEP/EMC and NHC, Regions (all but CR); NCEP/OPC OAR /Sea Grant; RFCs
Centralized Water Forecasting | Y |  |  |  | NWC: Don Clyne
FPAW (Friends and Partners of Aviation Weather) | Y |  | 18-19 August | P-Surge The next Psurge upgrade may include longer lead times, 5% exceedance, nested grid capability, and/or multiple simultaneous landfalls. | STI: Jason Chasse | FAA, NASA, UCAR/NCAR, ESRL | TBD
NextGen Aviation | Y |  |  |  | STI: Jason Chasse
Probabilistic Hazard Information Service |  |  |  |  | MDL: Mike Farrar, Dave Novak SPC: Russ Schneider(?)
National Blend of Models | Y | Limited set of prototype blended grids (Temperature and Dewpoint) developed for field evaluation, MDL developed viewer to facilitate improvements to analysis | 1. Add more gridded elements (PoP, MaxT, MinT, Wind speed/direction, Sky Cover, Apparent Temperature, Relative Humidity) and expand domains to OCONUS and Oceanic Winds. 2. Upgrade RTMA/URMA to provide improved analysis for verification, bias correction and calibration | Submitted proposal to Ming Ji to fund future phases of the National Blend | S. Lord. A. Friz. K. Gilbert, D. Myrick | MDL Base Funds from STI, submitted proposal for STI funds to expand scope of project, and CP funds to complete NCEP Center AWIPS II tool development for WPC | WFOs, NCEP Centers are stakeholders in National Blend development effort. All users of NDFD are stakeholders for improved consistency in our digital services | National Blend project has an Outreach team led by NWSEO representative Jim Sieveking. Project has and will be communicated through webinars, NWS national meetings, AMS and NWA meetings
VLAB | Y | 1. Portal installed and running. 2. Continuous updating process established. |  |  | MDL: Steve Smith
Impacts Catalog |  |  |  | 1. Testing and Evaluation | MDL:
CASA Urban Demonstration Network | Y |  | 1. Review meeting - TBD 2. Sensor deployment in Dallas 3. Data flow to WFO DAL | 1. Help with evaluation plans 2. Identify potential R2O results (along with NWC, SRH) 3. Coordinate OPG testing of any selected R2O items | STI: Tim McClung, Daniel Melendez, NWC: Ed Clark, OPG: Kim Runk. OBS: Curtis Marshall | $75k (GSD/Mesonet data buy contract) | OAR/NSSL, OFCM, NWS-Hydrology, STI, SRH, WFO DAL, SERFC, ESRL/GSD
Multifunction Phased Array Radar Risk Reduction |  | 1. SPY-1A shown to perform equal to or better than single-polarized NEXRAD. 3. Funding for follow on Advanced Technology Demonstrator (ATD) earmarked and advertised by FAA 2. Ten-Panel MIT/LL Demonstrator now at NSSL (dual pol phased array radar) | 1. Initial Analysis Readiness Decision (IARD) to select alternative and refine requirements and business case - 2018. 3. In-Service Decision (ISD) to address deployment activity if earlier decision favor such procurement - ca. 2026. 2. Final Investment Decision (FID) to finalize radar requirements, solicit/evaluate offers, and finalize business case - FY19. | 1. Follow progress of radar technology that could replace NEXRAD after SLEP. 3. Assist in evaluation of alternatives to occur between IARD and IID. 3. Select or comment on alternative selection for Initial Investment Decision. 2. Contribute NWS requirements to MPAR Business Case. | STI: Daniel Melendez, OBS: Mike Istok, NWC: Ed Clark, AFS: Bob Saffle | (OAR) | OAR/NSSL (Hondl); OFCM (Stailey); NWS/COO (Murphy); W/DCOS (Schlatter); OBS/ROC (Istok); AFS (Stern)
Tropical Program | Y | 1. HFIP 2. JHT 3. HWRF 4. Program Gap Assessment | 1. NOAA Hurricane Conference 2. HWRF next release by EMC ca. Dec2015/Jan2016 | 1. Participate in NOAA Hurricane Conference 2. Plan further R2O support to Tropical Program not limited to HFIP | 1. HFIP: Fred Toepfer 2. NWS HQ Tropical Program: AFS/Michael Dione 3. JHT: Chris Landsea 4. HWRF: Vijay Tallapragada | HFIP, JHT, NOS, NHC, OAR | NHC, NCEP, Coastal WFOs and RFCs, OAR/HRD, OAR/ESRL, W/IA
US GEO | Y | 1. Call for information from all US Govt agencies having observing systems. 3. Societal Benefit Areas (SBAs) identified and Team Leads assigned. 2. Organized socioeconomic categories for assessment in statistical model | Transition Assessment Working Group Earth Observing Assessment model (EOA) into Phase Two to assess progress of Societal Benefit Area teams | 1. Particpate in AWG meetings. 2. Provide NWS R2O analysis and assessment for EOA model development and validation | STI: Daniel Melendez; OBS: Kevin Schrabb | No | NESDIS, NWS/OBS, OAR/AOML, OMAO, NOS, NMFS
OFCM Atmospheric Transport and Dispersion (ATD) Joint Action Group | N | 1. STI co-led and participated in OFCM special session at GMU ATD Conference (yearly). 2. STI participated in past JAG meetings sponsored by OFCM. | 1. 2016 OFCM ATD Special Session as part of GMU Conference | 1. Participate in OFCM ATD JAG. 3. Provide input to GMU ATD Summary Report 2. Participate in GMU OFCM ATD Special Session | STI: I. Stajner, Melendez | NWS funds HYSPLIT, VAAC, Fire/Smoke monitoring and dispersion prediction. OFCM funds session. | NESDIS, NWS/OBS, OAR/Air Quality Lab, NOAA RSMC (VAASH, Chem/Nuc/Bio), NCEP/EMC | Continue supporting OFCM ATD coordination efforts as a function of the mission mandates of NWS
CSTAR/FSU | Y | Grant awarded - Improved Forecasting of Extrene Rainfall Events Associated with Tropical Cyclones (Fuelberg and Hart) |  |  | STI: Hedge | Yes | NHC
CSTAR/FIU | Y | Grant awarded - An Ensemble-Based Approach to Forecasting Surf, Set-Up, and Surge in the Coastal Zone (Lazarus and Weaver) |  |  | STI: Hedge | Yes | WFOs
NGGPS | Y | Four grants awarded: OU, Maryland, CPC, SUNY/ALBANY |  |  | STI: Hedge, Toepfer, Stajner | Yes | NCEP/EMC, NHC, CPHC, HRD
AMS Outreach |  |  |  | Gather data on STI staff engaged with AMS.
Note on A6: Daniel Melendez: No response has been received.